## Sheet1
CUCC Expedition Meeting Agenda
7pm 8th Janaury 2020
https://meet.jit.si/expo2019meeting
1) Review of Minutes & Actions from Last Meeting
| Action | Responsible
| Upload 2019 inventories to website | Harry
| Accounts to be published | Harry
| Coordination of drawing up the survey | Becka
| Upload expo poster | Nat
| Immediately scan the 2020 log book after expo | Haydon
| Sponsorship: Look at people we’ve pestered before, to share rejection list | Rachel
| Lydia to give the expo talk at CHECC, supported by Mike, Wob etc To include the mentoring system | Lydia
| Nadia to type up the mentoring system into something cohesive | Nadia
| Haydon to make the solar panel system transportable for Expo | Haydon
| Compile QM list to understand what are genuine leads Rob | Rob
| Sarah to work out if Slack is good for us | Sarah
| Becka and Shinwell to investigate Austrian storage solutions | Becka and Shinwell
| Clear out of Tatty Hut required | Everyone
| Evening dial in meeting, 8th January, 7pm (GMT) | Lydia to arrange
| Agenda to include fixing dates. Lydia and Mike to fix | Lydia/Mike to fix agenda
| Doodle poll for ideal expedition dates and length | Becka
2) Progress Report of Jobs/Roles
| Job roles | Responsible person
| Expo Leaders: | Lydia and Mike
| Treasurer: | Dickon
| Rigging Guide: | Mark Docherty
| T Shirts: | Radost
| Website: | Anthony, Wookey, Alice
| Gear Coordination in Cambridge: | Crossley and Vassil
| Gear Order | Harry and Chris Densham
| Food Order: | Nat and Sarah
| Transport Plan: | Pete Talling
| Surveys: | Becka
| Training Weekend: | Fleur to lead
| Flapjack Volunteers: | EVERYONE
| Survex: | Olly Betts
| Technical Charging and Drills: | Frank Tully
| Sponsorship: | Dickon and Mike
| Austrian liaison: | Shinwell and Elaine
3) Dates of Expedition
4) Objectives of Expedition
5) Mentoring System
6) Pre-Expedition Weekends:
Social weekend 21st/23rd February @ TSG
Training weekend To Be Arranged
7) Equipment
Hangers - Antony Day
8) Any Other Business